## Business case
Business case — exception management (option O3)
Illustrative assumptions for a fictional organisation — not real company data. Yellow cells are inputs; everything else is calculated.
Inputs
WISMO contacts per week | 1250 | contact-reason tagging, 2 weeks
Handling time per contact (min) | 6 | telephony report
Loaded cost customer service (EUR/h) | 42 | finance
Expected WISMO reduction | 35% | riskiest assumption — measured in the pilot
Missed delivery slots per week | 55 | planner log + credit notes
Cost per missed slot (EUR) | 140 | credit notes, 3 months
Expected missed-slot reduction | 30% | planning lead estimate
Weeks per year | 50
Sprint cost (EUR, team of 8 for 2 weeks) | 38000
Sprints (R1 + R2) | 4 | R1 = 2 sprints, R2 = 2 sprints
TMS supplier set-up (EUR) | 25000 | quote
Notification set-up (EUR) | 8000 | estimate
BAT, training, pilot support (EUR) | 10000 | 2 x 5k
Yearly running cost (EUR) | 34000 | API licence 18k + 0.2 FTE support 16k
Results
CS hours per week on WISMO
Benefit: customer-service time (EUR/yr)
Benefit: fewer missed slots (EUR/yr)
Total benefits (EUR/yr)
One-off cost (EUR)
Net benefit (EUR/yr)
Payback (months)
Release 1 pilot cost (EUR)

## Sensitivity
Sensitivity — the riskiest assumption
Illustrative assumptions for a fictional organisation — not real company data.
Scenario | WISMO reduction | Missed-slot reduction | Benefits / year (EUR) | Net / year (EUR) | Payback (months)
Pessimistic | 20% | 15%
Expected | 35% | 30%
Optimistic | 50% | 40%
Pilot readout (illustrative) | 26% | 21%
Stage gate (D-07): fund release 2 if WISMO reduction against the control group is at least 20%.

## Options
Option scoring (1 = poor, 5 = good) — weights agreed before scoring
Criterion | Weight | O1 Do nothing + agent | O2 Standard TMS e-mails | O3 Exception management | O4 Visibility platform
Fixes the root cause | 30% | 1 | 2 | 5 | 3
Customer experience | 25% | 2 | 2 | 4 | 5
Cost over 3 years | 20% | 3 | 5 | 3 | 1
Delivery risk / dependency | 15% | 5 | 4 | 3 | 2
Fit with the new TMS | 10% | 3 | 4 | 4 | 2
Weighted score

## Backlog WSJF
Backlog — WSJF = (business value + time criticality + risk reduction/enablement) / size
ID | Item | Business value | Time criticality | Risk reduction / enablement | Size (pts) | Cost of delay | WSJF | Release
EN-2 | Delivery window mandatory for pilot customers | 2 | 5 | 8 | 1 |  |  | R1
US-07 | No message storm (throttling) | 5 | 5 | 8 | 2 |  |  | R1
US-13 | Pilot toggle and measurement | 3 | 8 | 13 | 3 |  |  | R1
EN-1 | Receive TMS changes reliably | 1 | 8 | 13 | 3 |  |  | R1
US-02 | Owner and response time | 5 | 3 | 5 | 2 |  |  | R1
US-05 | Proactive customer message | 13 | 8 | 8 | 5 |  |  | R1
US-04 | Acknowledge, re-plan, resolve | 5 | 3 | 8 | 3 |  |  | R1
US-08 | Missing status: confirm first | 5 | 3 | 8 | 3 |  |  | R1
US-01 | Classify a change | 8 | 5 | 13 | 5 |  |  | R1
US-11 | Call task for key accounts | 5 | 3 | 2 | 2 |  |  | R1
US-10 | Back on schedule | 3 | 2 | 3 | 2 |  |  | R1
US-03 | Workbench (list + escalation) | 8 | 5 | 5 | 5 |  |  | R1
US-09 | Customs hold, action required | 5 | 2 | 3 | 5 |  |  | R2
US-06 | EDI/API status messages | 8 | 3 | 3 | 8 |  |  | R2
US-12 | Notification preferences in the portal | 3 | 1 | 2 | 5 |  |  | R2
US-14 | Consignee notifications | 8 | 1 | 2 | 13 |  |  | R3
Release 1 points

## BAT log
Business Acceptance Testing — execution log (simulated)
ID | Scenario | Key user | Stories | Run 1 | Finding | Retest | Final
BAT-01 | Sailing with 20 orders delayed 6 h | planner | US-01, US-03 | pass |  |  | pass
BAT-02 | 8 situations from last month | planner, CS | US-01, US-02 | pass | 1 rule question (consignee hours) → R2 |  | pass
BAT-03 | Untouched critical escalates | shift lead | US-03 | pass | DEF-05 (minor, known issue) |  | pass with known issue
BAT-04 | Acknowledge, new window, resolve | planner | US-04 | fail | DEF-03 (minor) | pass | pass
BAT-05 | No status for 7 h | planner | US-08 | pass |  |  | pass
BAT-06 | Critical for key account | AM, CS | US-11 | pass | DEF-06 (minor, known issue) |  | pass with known issue
BAT-07 | Customer reads the message | pilot customer | US-05 | fail | DEF-01 (major) | pass | pass
BAT-08 | Three sailing updates in 10 min | planner, pilot customer | US-07 | fail | DEF-04 (major) | pass | pass
BAT-09 | Order without a window | planner | US-01 | fail | DEF-02 (major) | pass | pass
BAT-10 | Notified delay recovers | pilot customer | US-10 | pass |  |  | pass
BAT-11 | Pilot export, shadow mode | PO | US-13 | pass |  |  | pass
BAT-12 | Bounced address | CS | US-05 | pass |  |  | pass
Passed in run 1
Accepted (final)

## Traceability
Traceability — pain point to KPI
Pain | Business req. | Functional / NFR | Rules | Stories | Tests | KPI
P1 ETAs not updated, nobody evaluates | BR-1 | FR-01, FR-03, NFR-01 | ER-01 | US-01 | AC-01.1–01.2, BAT-01 | K2
P2 noticed by chance | BR-4 | FR-02, FR-04, FR-07 | ER-02–ER-05, ER-08, ER-09 | US-02, US-03 | AC-01.3–01.12, AC-02.1, BAT-02, BAT-03 | K6
P3 Excel lookup | BR-4 | FR-04 | ER-08 | US-03 | BAT-03 | guardrail workload
P4 only key accounts whose AM knows | BR-1 | FR-06, FR-13 | ER-10, ER-11 | US-05, US-11 | AC-11.1–11.3, BAT-06 | K1
P5 customer finds out at the slot | BR-1, BR-2 | FR-06, FR-10, FR-11 | ER-10, ER-12, ER-13 | US-05, US-07, US-10 | AC-07.1–07.5, AC-10.1–10.2, BAT-07, BAT-08, BAT-10 | K1, K3, K8
(new) false alarms on missing status | BR-4 | FR-08 | ER-07 | US-08 | AC-08.1–08.4, BAT-05 | K7
P6 nothing recorded | BR-5 | FR-05, FR-12 | — | US-04, US-13 | BAT-04, BAT-11 | reason completeness
missed slots | BR-3 | FR-05 | ER-03 | US-04 | AC-01.9, BAT-04 | K4, K5